Steps taken during an upgrade

FROM Bob on Trello card Client Upgrade Template

This is a new check list to give you an overview of what steps are taken within SPC for a new or upgrade client.

- SPC contract signed

- Unforeseen Cost Fund initialed

- Survey Scheduled - Alex

- Maps Received - Alex

- FM Audit installed - Alex

- STAR Doc built and maps upload - Alex

- Electronic Surveys Built --James/Jamin

- Survey Completed and assigned in Google to BM & IT- Alex/Jamin

- Survey data entered into Access - Jamin

- FYERS to be built - Skip/Alex

- Compare Built - James

- Schedule FYERS review with customer - Alex

- FYERS reviewed with customer - Skip/Alex

- FYERS approved by customer - Skip/Alex

- Bids sent to Vendor - Skip/Alex

- Schedule bid results review with client - Alex

- Vendor Awarded & Other Vendors Notified - Skip/Alex

- Equipment Ordered - Jessica

- Vendor meeting scheduled - Alex

- Work Orders Created and sent to customer - Alex

- Date set for install - Alex

- Equipment Installed - Alex/Jamin

- Audit Finalized and Posted - Alex/Jamin

- Close-out meters entered into DMS - Jamin/Pam

- Close-out Reconciliation Reports run and posted for Jessica - Pam

- Import upgrade data into DMS - Pam/Alex

- Upgrade Pre-Bill Reports run and posted for Jessica - Pam

- STARDoc and FM Audit updated with new information - James

- Upgrade Report Scheduled - Pam

- Upgrade Report Presented - Alex